## schedule
Task	Estimate		Rate	$45.00
Investigate commonly used web-app development frameworks	4
Investigate web-app communication to Arduino	4
Write web-app serial communication code	16
Write Arduino client side serial communication code	8
Write Arduino interrupt code to poll for serial communication	8
Update Assessments to check for serial communication	6
Build up web-app User facing code	16
Build up web-app Admin facing code	16
Investigate database setup on Windows	4
Link database to app	16
Write unit tests for web-app code	16
Create a Windows installer for web-app and db	12
Total Hours	126

Total	$5,670.00

## electron installation
Electron installation

download/install node.js from nodejs.org/en
cd into project dir
npm init
follow prompts, defaults are fine for most questions

install python

npm install –save-dev electron-rebuild
npm install
add install hook for electron-rebuild in package.json

## qualtrics questions
REST API?
How to authenticate to Qualtrics?
What info needs pulled from server? List of sites, token?

## serial cmds
Serial Commands Table

Command	Description	Command Data	Response Data
RST	Initiate a soft-reset of Arduino		RDY string loop (same as after hard reset)

GFW	Get Arduino FW Version		Arduino FW Version

SA1A	Start Assessment 1A		Score
SA1B	Start Assessment 1B		Score
SA2	Start Assessment 2		Score
SA3	Start Assessment 3		Score

ST1A	Stop Assessment 1A		Score
ST1B	Stop Assessment 1B		Score
ST2	Stop Assessment 2		Score
ST3	Stop Assessment 3		Score

GR1A	Get Assessment 1A Result		Score
GR1B	Get Assessment 1B Result		Score
GR2	Get Assessment 2 Result		Score
GR3	Get Assessment 3 Result		Score

RS1A	Reset Assessment 1A
RS1B	Reset Assessment 1B
RS2	Reset Assessment 2
RS3	Reset Assessment 3